## At a glance
Phase B — Rollout Runbook
Generated | 2026-05-22
Source artifacts | ~/Documents/HealthPulse-Lovable/
Target environment | Lovable Cloud — vital-insights-studio.lovable.app
Apply order | 001 → 002 → 003 → 004 → 006 → (optional 005) → Edge Function → UI scaffolds → smoke tests
Total estimated time | 30–60 minutes if everything goes smoothly; budget 2h with buffer
Rollback strategy | Each migration file has a ROLLBACK section at its bottom. Apply in reverse order. No dependency cycles.
Backout point | After 003 applies, moderators lose audit visibility — communicate before this step or revert if needed.
Pre-flight checks (do these before starting)
☐ Confirm you are signed into Lovable Cloud as an org admin of Demo Hospital (org_id 00000000-0000-0000-0000-000000000001). The migrations use private.is_org_admin checks; you need admin privileges to test post-apply.
☐ Open Lovable Cloud's SQL editor in one tab and the live app (vital-insights-studio.lovable.app) in another. You'll alternate between them.
☐ Take a current pg_policies snapshot for metric_audit_log so you have a baseline if 003 needs rollback. Save the output somewhere accessible.
☐ Verify your admin@example.com account is currently the only admin in org_members for Demo Hospital. If you accidentally lose admin access mid-migration (the change_member_role guards prevent self-demotion, but accidents happen), you'll need DB-direct access to recover.
☐ Decide upfront: are you applying migration 005 (hashed tokens) today or later? If later, plan to skip it and revisit after Phase B v1 is stable.
☐ Have edge-functions/send-invite/index.ts open in your editor — you'll deploy it after migration 002 lands.

## Apply sequence
Step | Action | File / target | Expected output | If it fails | Time
0 | Pre-flight checks complete (see 'At a glance' sheet) | — | All 6 boxes ticked | Don't start until they are. The communication-before-003 item is the most overlooked. | 10m
1 | Apply migration 001 | migrations/001_org_invites_and_predicate.sql → Lovable Cloud SQL editor | Success messages: CREATE FUNCTION, CREATE EXTENSION, CREATE TABLE, 3 × CREATE INDEX, ALTER TABLE ENABLE ROW LEVEL SECURITY, 4 × CREATE POLICY, REVOKE, GRANT. | If CREATE TABLE errors with 'relation org_invites already exists' — table exists from a partial earlier apply. Drop it (DROP TABLE public.org_invites CASCADE;) and re-run. If 'function private.has_role does not exist' — Phase A migration drift; check pg_proc for has_role. | 3m
2 | Verify 001 — table + RLS | SQL editor | SELECT count(*) FROM public.org_invites; -- expect 0 SELECT policyname, cmd, permissive FROM pg_policies WHERE tablename='org_invites'; -- expect 4 rows: 1 PERMISSIVE SELECT (admin), 3 RESTRICTIVE deny on INSERT/UPDATE/DELETE | If only the SELECT policy shows — the RESTRICTIVE writes didn't apply. Re-run the CREATE POLICY blocks from 001 individually. | 2m
3 | Apply migration 002 | migrations/002_invite_and_member_functions.sql → SQL editor | 6 × CREATE FUNCTION (create_org_invite, revoke_org_invite, preview_invite, accept_org_invite, change_member_role, remove_org_member), each followed by REVOKE + GRANT. | If 'function public.organizations does not exist' — the org name lookup in preview_invite failed. We confirmed public.organizations exists on 2026-05-21, but if the schema has drifted, edit preview_invite to skip the SELECT or use a different source. | 3m
4 | Verify 002 — functions exist | SQL editor | SELECT proname, prokind FROM pg_proc WHERE pronamespace = 'private'::regnamespace AND proname IN ('create_org_invite','revoke_org_invite','preview_invite','accept_org_invite','change_member_role','remove_org_member'); -- expect 6 rows, all prokind='f' | Missing function → re-run that specific CREATE OR REPLACE block from 002. | 2m
5 | COMMUNICATE BEFORE 003 — audit visibility change | Slack / email to existing org members (if any beyond you) | Message: 'In about 5 minutes, moderators and read-only users will lose visibility into the audit log. Admins retain full access via the new Settings → Audit Log page. Reply by [time] if this blocks anything.' | If anyone objects, switch to the 'self-audit' variant in 003 instead (uncomment the alternate USING expression). | 5m + wait window
6 | Apply migration 003 | migrations/003_tighten_audit_log_select.sql → SQL editor | NOTICE messages like: 'Phase B / 003: dropping existing PERMISSIVE SELECT policy: <whatever name>'. Then DROP POLICY + CREATE POLICY + COMMENT ON POLICY messages. | If no NOTICE fires, the table had no PERMISSIVE SELECT — unusual but not fatal. Continue to verification step. | 2m
7 | Verify 003 — audit RLS tightened | SQL editor | SELECT policyname, cmd, permissive, qual FROM pg_policies WHERE tablename='metric_audit_log'; -- expect 1 PERMISSIVE SELECT named 'audit_select_admin' using private.is_org_admin(org_id), plus 3 RESTRICTIVE write denies. | Wrong qual → re-run the DROP+CREATE block from 003. | 1m
8 | Spot-check 003 from the live app | vital-insights-studio.lovable.app | As moderator (current account), try to read metric_audit_log via PostgREST: open browser console, run a fetch like the verification did. Expect RLS-denied rows (0 returned). If you happen to have an admin in this org, sign in as them — they should see rows. | If moderators still see rows — the old policy may not have been dropped. Re-check pg_policies. | 5m
9 | Apply migration 004 | migrations/004_list_org_members.sql → SQL editor | CREATE FUNCTION public.list_org_members + REVOKE + GRANT + COMMENT. | If 'column om.created_at does not exist' — the org_members table uses a different column name. Edit the SELECT in 004 per the note in the file. | 2m
10 | Verify 004 — RPC callable | SQL editor or via PostgREST | SELECT * FROM public.list_org_members('00000000-0000-0000-0000-000000000001'); -- expect 1+ row(s) with user_id, email, role, joined_at columns | If 'forbidden: caller is not an admin' — you ran this as a non-admin role in the SQL editor. SQL editor typically runs as service_role; that should bypass. Check who you're authed as. | 2m
11 | Apply migration 006 — perf indexes | migrations/006_audit_log_perf_indexes.sql → SQL editor | 3 × CREATE INDEX (org+created_at, org+user_id+created_at, org+metric_date). | If 'index already exists' — IF NOT EXISTS handles this silently. If 'permission denied' — check role. | 2m
12 | OPTIONAL — Apply migration 005 (hashed tokens) | migrations/005_OPTIONAL_hash_invite_tokens.sql → SQL editor | Skip if you decided in pre-flight to defer. If applying: ADD COLUMN, UPDATE backfill, ALTER NOT NULL, CREATE INDEX, DROP COLUMN, then 3 × CREATE OR REPLACE FUNCTION. | Bug we caught and fixed: the DROP COLUMN happens BEFORE the function replacements. If you see 'column token does not exist' during function creation, something's wrong with the file — verify the order. | 5m
13 | Deploy send-invite Edge Function | edge-functions/send-invite/index.ts → Lovable Cloud Edge Functions | Function appears in the project's Edge Functions list. Set env vars: APP_URL=https://vital-insights-studio.lovable.app and (if using Resend fallback) RESEND_API_KEY + RESEND_FROM_EMAIL. | If Lovable Cloud doesn't let you set service_role-aware Edge Functions, fall back to a Supabase CLI deploy. The function code is provider-agnostic Deno. | 10m
14 | Wire UI scaffolds into Lovable | ui-scaffolds/* → adapt into Lovable's builder | /settings/members loads (admin sees members + invites lists), /settings/audit loads (admin sees filtered table + diff modal), /invite/[token] loads (renders the 5 states correctly). | Lovable's builder may want React Router paths phrased differently. Adapt as needed; the page logic is what matters. | 30m + adaptation
15 | Smoke test — invite happy path | Live app | Sign in as admin → /settings/members → invite a throwaway email → check email arrives → click link → /invite/[token] renders → accept → land in /command as the new member. | If email doesn't arrive: check Edge Function logs in Lovable Cloud. If both Supabase Auth and Resend paths fail: copy the accept URL from the pending invite row and share manually. | 10m
16 | Smoke test — audit viewer | Live app | Sign in as admin → /settings/audit → see today's activity (including your own throwaway invite test row). Open the diff modal on a recent row → before/after JSON renders with yellow highlight on changes. | If 0 rows show: confirm the date range filter is wide enough; default is last 30d. | 5m
17 | Phase B verification run | Run tests T1–T16 from the plan workbook 'Test Cases' sheet | All 16 pass (T15/T16 are mutually exclusive based on which email path your deploy uses). | Failed tests → file in the verification log; decide which need fixes-now vs. Phase B.1. | 30m
18 | Update memory + close out | SECURITY_MEMORY.md — append a Phase B close section | Memory has: Phase B publish date, applied migrations list, smoke test outcomes, deferred Phase C items. | — | 5m

## Rollback paths
Trigger | What broke | Rollback steps (in order) | Data loss risk
003 breaks moderator audit access and they need it back | Moderators report they can't see audit history; an admin agrees this should not have been tightened | 1. Apply the ROLLBACK section at bottom of 003 (recreates is_org_member SELECT) 2. Verify via pg_policies that audit_select_member is back 3. Communicate restoration to affected users | None — audit log rows themselves are untouched.
002 has a bug in one of the functions | Invite creation/acceptance/role-change errors in production | 1. Identify which function (error message) 2. Run DROP FUNCTION private.<name>(...) 3. Either re-CREATE the prior good version OR re-CREATE from 002 after fixing 4. If the broken function corrupted org_members, restore from logical backup | Possible — if change_member_role or remove_org_member corrupted org_members rows. Phase A's audit trigger on org_members (if you added one — it was optional) would document the change.
001's org_invites table needs to be removed entirely | You decide to abandon the invites flow | 1. DROP TABLE public.org_invites; (cascades indexes + policies) 2. DROP FUNCTION private.is_org_admin(uuid); (if no other migration uses it) 3. Note: leave the citext extension in place — harmless if unused 4. Revert the UI scaffolds (don't deploy /settings/members) | Loss of any pending invite rows (which are still useful only as a historical record). Already-accepted members in org_members stay; nothing breaks.
005 (hashed tokens) was applied and you want plaintext back | Switching back to plaintext token storage | 1. ALTER TABLE public.org_invites ADD COLUMN token text; 2. DROP INDEX org_invites_token_hash_idx; 3. ALTER TABLE public.org_invites DROP COLUMN token_hash; 4. Re-CREATE OR REPLACE the create_org_invite / preview_invite / accept_org_invite function bodies from 002 | All outstanding invites become unusable — tokens can't be recovered from hashes. Revoke + reissue any pending invites.
send-invite Edge Function deployed but emails not arriving | Email delivery silently fails | 1. Check Edge Function logs in Lovable Cloud — look for 'supabase_failed_and_no_resend' or 'resend_failed' responses 2. If Supabase path is blocked, add RESEND_API_KEY env var 3. If both fail, members.tsx UI has a fallback: copy the accept URL from the pending invite row and share manually 4. As emergency: surface a 'Copy link' button next to each pending invite | None — invites still exist, just no auto-email.
UI scaffolds break the existing routes | Path conflicts after adapting scaffolds into Lovable's builder | 1. Revert the UI deploy in Lovable Cloud (use the project history / undo) 2. DB migrations stay applied — they're independent 3. Iterate on scaffolds offline before retrying | None — pure UI revert.
Phase A regression — Test 2 (forge attempt) now succeeds | Migration 003 accidentally loosened RESTRICTIVE writes on metric_audit_log | 1. Inspect pg_policies for metric_audit_log — confirm the 3 RESTRICTIVE policies are still in place 2. If missing, re-CREATE them from the Phase A migration history 3. Re-run Phase A Test 2 (PostgREST forge attempt) to confirm 42501 | If audit writes were happening from non-trigger sources during the window, those rows are now in the table. Inspect for created_at clustering near the 003 apply time + actor patterns that don't match the trigger.

## Post-apply smoke
# | Test | How to run | Expected | Ties to T-test
S1 | is_org_admin predicate works | SQL editor as your admin account: SELECT private.is_org_admin('00000000-0000-0000-0000-000000000001'); | true | —
S2 | create_org_invite issues a token | SQL editor: SELECT private.create_org_invite('00000000-0000-0000-0000-000000000001'::uuid, 'smoke-test@example.com', 'user'::app_role); -- returns invite uuid (or { invite_id, token } if 005 applied) SELECT id, email, token, expires_at FROM public.org_invites WHERE email='smoke-test@example.com'; | Row exists, token present (or token_hash present if 005), expires_at ~7 days out. | T15 setup
S3 | preview_invite returns safe fields only | SQL editor: SELECT private.preview_invite('<the-token-from-S2>'); | jsonb with status='valid', org_name='Demo Hospital', role='user', email, expires_at. NO id, token, or org_id leakage. | T15
S4 | accept_org_invite rejects mismatched email | From a session signed in as you (admin@example.com): SELECT private.accept_org_invite('<token>'); | Error: 'email_mismatch: signed-in email does not match the invitee' | T5
S5 | revoke_org_invite is idempotent | SQL editor: SELECT private.revoke_org_invite('<invite-id-from-S2>'); SELECT private.revoke_org_invite('<same-invite-id>'); -- call twice | Both calls succeed (second is no-op). Row now has revoked_at set. | T4
S6 | change_member_role last-admin guard | SQL editor: SELECT private.change_member_role('<your-user-id>'::uuid, '00000000-0000-0000-0000-000000000001'::uuid, 'moderator'::app_role); | Error: 'last_admin: cannot demote the only admin of this org' (assuming you're the only admin) | T7
S7 | Audit RLS tightening — moderator can't read | Sign in as a moderator (or downgrade a test account, then re-elevate): fetch('/rest/v1/metric_audit_log?select=*&limit=1', { headers }) in browser console | Empty array (RLS denied SELECT). | T10
S8 | Audit RLS — admin can read own org | Sign in as admin, same fetch. | 1+ rows returned. All have org_id matching admin's org. | T11
S9 | Cleanup the smoke test row | SQL editor: DELETE FROM public.org_invites WHERE email='smoke-test@example.com'; | 1 row deleted. | —

## Final inventory
File | Lines | Purpose
migrations/001_org_invites_and_predicate.sql | 120 | is_org_admin predicate + org_invites table + RLS
migrations/002_invite_and_member_functions.sql | 393 | 6 SECURITY DEFINER functions for invites + member mgmt
migrations/003_tighten_audit_log_select.sql | 90 | Tighten metric_audit_log SELECT → admins only (name-agnostic DO block)
migrations/004_list_org_members.sql | 64 | Helper RPC joining auth.users.email for admin pages
migrations/005_OPTIONAL_hash_invite_tokens.sql | 270 | OPTIONAL: hash invite tokens at rest
migrations/006_audit_log_perf_indexes.sql | 60 | 3 composite indexes on metric_audit_log for /settings/audit
edge-functions/send-invite/index.ts | 228 | Deno Edge Function: Supabase Auth invite first, Resend fallback. Forward-compatible with 005.
ui-scaffolds/settings/members.tsx | 378 | Admin Members page: list, invite, role change, remove
ui-scaffolds/settings/audit.tsx | 295 | Admin Audit viewer: filters, diff modal, CSV export
ui-scaffolds/invite/[token].tsx | 271 | Public invite acceptance landing with 5-state machine
phase-b-plan-2026-05-21.xlsx | — | Design-time plan: schema, RLS, functions, UI surfaces, migration order, test cases
phase-b-rollout-runbook.xlsx | — | Rollout-time: apply sequence, rollback paths, smoke tests
verification-2026-05-21.xlsx | — | Phase A live verification record
SECURITY_MEMORY.md (in ~/.claude/projects/...) | — | Phase A close + Phase B live verification log