## Overview
HealthPulse Phase B — Plan
Drafted | 2026-05-21
Author | Prabhu + Claude verification pass
Phase A status | Published 2026-05-20 to vital-insights-studio.lovable.app; all 3 accepted scanner findings verified live 2026-05-21
Phase B scope | B1 (Invites + Admin Console) + B2 (Audit Log Viewer)
Email delivery | Try Supabase Auth inviteUserByEmail via Edge Function first; fallback to Resend if Lovable Cloud blocks it
Audit SELECT tightening | Yes — drop is_org_member SELECT on metric_audit_log, add is_org_admin SELECT
Goals
• Real onboarding: admins invite by email; invitees accept via link; new member lands in org_members with the right role. Replaces the manual private.promote_org_member SQL workflow.
• Compliance UX: admins can read metric_audit_log via UI with filters and before/after diffs. No SQL editor required.
• Privacy tightening: non-admin org members can no longer read audit history (it's an admin/officer responsibility).
• Preserve Phase A security posture: open-signup hardening stays in place; signup is only contextually exposed inside the invite-acceptance flow.
Out of scope (defer to Phase C)
• Multi-org membership / org switcher
• Per-org alert rule configuration (currently rules are hardcoded in Command Center)
• Notification routing to email / Slack / PagerDuty when thresholds breach
• Audit log retention policy / archival
• CSV import hardening (the /metrics CSV Import tab)

## Schema
Object | Definition | Notes
public.org_invites (new table) | id uuid PK default gen_random_uuid() org_id uuid NOT NULL email citext NOT NULL role app_role NOT NULL token text NOT NULL UNIQUE expires_at timestamptz NOT NULL default now() + interval '7 days' accepted_at timestamptz revoked_at timestamptz created_by uuid NOT NULL references auth.users(id) created_at timestamptz NOT NULL default now() | token is a 32-byte random string (base64url). Consider hashing at rest if you want defense in depth — store hash, send raw in email, look up by hash on accept.
Index: org_invites_token_idx | CREATE UNIQUE INDEX org_invites_token_idx ON public.org_invites (token); | Fast lookup by token for accept_org_invite().
Index: org_invites_org_email_active | CREATE UNIQUE INDEX org_invites_org_email_active ON public.org_invites (org_id, email) WHERE accepted_at IS NULL AND revoked_at IS NULL; | Prevents two open invites to the same email for the same org. New invite forces revoke or accept of the old one.
Index: org_invites_org_id_idx | CREATE INDEX org_invites_org_id_idx ON public.org_invites (org_id) WHERE accepted_at IS NULL AND revoked_at IS NULL; | Drives the admin's Pending Invites list.
ALTER metric_audit_log RLS | DROP POLICY "audit_select_member" ON public.metric_audit_log; CREATE POLICY "audit_select_admin" ON public.metric_audit_log FOR SELECT TO authenticated USING (private.is_org_admin(org_id)); | Tightens SELECT to admins. Existing RESTRICTIVE deny on writes stays unchanged.
Optional: trigger on org_members | CREATE TRIGGER write_member_audit AFTER INSERT OR UPDATE OR DELETE ON public.org_members FOR EACH ROW EXECUTE FUNCTION private.write_member_audit(); Function writes to a new public.member_audit_log table (or appends to a generalized audit log) so role changes / invites accepted / removals are tamper-evidently logged. | Recommended. Without this, invite acceptances and role changes aren't on the audit trail. Could also unify into a single audit log table keyed by (table_name, record_id) — judgment call.

## RLS Policies
Table | Command | Type | Roles | Expression | Notes
org_invites | SELECT | PERMISSIVE | authenticated | USING private.is_org_admin(org_id) | Admins see invites for their own org.
org_invites | INSERT | RESTRICTIVE | authenticated, anon | WITH CHECK (false) | All client INSERTs denied. Creation only via private.create_org_invite SECURITY DEFINER.
org_invites | UPDATE | RESTRICTIVE | authenticated, anon | USING (false) | All client UPDATEs denied. Acceptance/revocation only via SECURITY DEFINER functions.
org_invites | DELETE | RESTRICTIVE | authenticated, anon | USING (false) | Soft-delete via revoked_at instead. Hard DELETE blocked.
metric_audit_log | SELECT | PERMISSIVE | authenticated | USING private.is_org_admin(org_id) | Tightened from is_org_member. Non-admins can no longer browse audit history.
metric_audit_log | INSERT/UPDATE/DELETE | RESTRICTIVE (unchanged) | authenticated, anon | WITH CHECK / USING (false) | Phase A property preserved. Only the write_metric_audit trigger writes.
org_members | (unchanged) | — | — | — | No client writes. Mutations via private.promote_org_member, private.change_member_role, private.remove_org_member, private.accept_org_invite.

## Functions
Function | Signature | Returns | Guards (internal checks) | Logic summary | Grants
private.is_org_admin | is_org_admin(p_org_id uuid) | boolean | n/a (predicate) | Returns true if auth.uid() has 'admin' role AND is a member of p_org_id. Used by RLS policies and other functions. | EXECUTE granted to authenticated.
private.create_org_invite | create_org_invite(p_org_id uuid, p_email text, p_role app_role) | uuid (invite id) | is_org_admin(p_org_id); p_role IN ('admin','moderator','user'); revoke any existing open invite for (p_org_id, p_email) first | Generate 32-byte token (base64url). Insert org_invites row with token, expires_at = now()+7d. Return new invite id. Caller fetches the row to read token for email send. | EXECUTE granted to authenticated. SECURITY DEFINER.
private.revoke_org_invite | revoke_org_invite(p_invite_id uuid) | void | is_org_admin(invite.org_id); invite is not already accepted/revoked | Set revoked_at = now() on the invite. No row delete. | EXECUTE granted to authenticated. SECURITY DEFINER.
private.preview_invite | preview_invite(p_token text) | jsonb { org_name, role, email, expires_at, status } | Lookup-only; no auth required because tokens are unguessable | Resolve invite by token. Return ONLY org_name, role, email, expires_at, and status enum {valid, expired, revoked, accepted}. Never return token, org_id, created_by, or invitee user_id. Allows /invite/[token] to render before sign-in. | EXECUTE granted to anon, authenticated. SECURITY DEFINER.
private.accept_org_invite | accept_org_invite(p_token text) | jsonb { org_id, role } | Token exists; expires_at > now(); revoked_at IS NULL; accepted_at IS NULL; lower(invite.email) = lower(auth.email()) | Insert into org_members (auth.uid(), invite.org_id, invite.role) ON CONFLICT (user_id, org_id) DO UPDATE SET role = invite.role. Set accepted_at = now() on the invite. Return { org_id, role }. | EXECUTE granted to authenticated. SECURITY DEFINER.
private.change_member_role | change_member_role(p_user_id uuid, p_org_id uuid, p_new_role app_role) | void | is_org_admin(p_org_id); NOT (p_user_id = auth.uid() AND p_new_role <> 'admin') -- prevent self-demotion lockout; NOT (current state has p_user_id as last admin AND p_new_role <> 'admin') | Update org_members.role for (p_user_id, p_org_id). | EXECUTE granted to authenticated. SECURITY DEFINER.
private.remove_org_member | remove_org_member(p_user_id uuid, p_org_id uuid) | void | is_org_admin(p_org_id); p_user_id <> auth.uid() -- can't remove self; NOT (p_user_id is the only admin in p_org_id) | DELETE FROM org_members WHERE user_id = p_user_id AND org_id = p_org_id. (Consider soft-delete with removed_at column instead — Phase C decision.) | EXECUTE granted to authenticated. SECURITY DEFINER.

## UI Surfaces
Page / path | Audience | Components | States / Edge cases | Notes
/settings/members | Admins only | Members table (email, role badge, joined date, role-change dropdown, [Remove] button) Pending invites table (email, role, sent, expires in, [Resend] [Revoke]) Invite form (email input, role select, [Send invite] button) | Loading skeleton for both tables. Mutation toasts on every action. Disable role-change if it would self-demote or demote last admin (server returns 4xx). Disable Remove on self. Resend regenerates token + extends expires_at. | Non-admins land here -> redirect to /command with 'You don't have access' toast.
/settings/audit | Admins only | Filter bar: date range (default last 30d), action (chip multi-select: create/update/delete), user (autocomplete from org members), metric_date (date picker) Table: created_at, actor (email), action chip, metric_date, [View diff] Diff modal: side-by-side JSON with changed keys highlighted in yellow [Export CSV] button | Pagination 50/page with server-side range header. Empty state: 'No audit entries for this filter.' CSV export uses existing escapeCsvCell sanitizer. | Joining actor email requires either (a) projecting user_id -> email via a SECURITY DEFINER RPC, or (b) a view that joins auth.users restricted to org members. Pick (a) — less surface area.
/invite/[token] | Public (no auth gate to view) | Calls private.preview_invite(token) on load. Renders org name + role + invitee email. State machine: valid + not signed in -> 'Sign in as <email>' or 'Create account as <email>' valid + signed in as right email -> [Accept invitation] button valid + signed in as different email -> 'Please sign out and sign in as <email>' expired -> message + 'Ask your admin for a new invite' revoked -> message + 'Contact your admin' accepted -> message + 'Sign in to continue' | On Accept -> call accept_org_invite(token). On success -> toast + redirect /command. On failure -> error toast with reason from RPC. | Signup unblock: only here can a new user create an account, and supabase.auth.signUp options.emailRedirectTo points back to /invite/[token] so they land here after email verification, signed in.
Sidebar nav update | Admins see extra entries | Under Settings, add sub-items: 'Members' -> /settings/members; 'Audit Log' -> /settings/audit. Or add a top-level 'Admin' group visible only when role='admin'. | Non-admin sessions: nav items hidden (defense-in-depth; server-side RLS is the real gate). | Consistent with current sidebar styling (HealthPulse uses lucide icons; pick UserPlus for Members and ScrollText for Audit Log).

## Migration Order
Step | Type | Action | Depends on | Rollback plan | Risk
1 | DB migration | Create table public.org_invites with columns, indexes, and the 4 RLS policies (admin SELECT, RESTRICTIVE writes). | — | DROP TABLE public.org_invites; revoke nothing else. | Low — additive only.
2 | DB migration | Create private.is_org_admin, create_org_invite, revoke_org_invite, preview_invite, accept_org_invite, change_member_role, remove_org_member. REVOKE EXECUTE FROM PUBLIC; GRANT EXECUTE to authenticated (preview_invite also to anon). | Step 1 | DROP FUNCTION ... (all 7). | Low — additive; no behavior change in app yet.
3 | DB migration | Tighten metric_audit_log SELECT: DROP audit_select_member; CREATE audit_select_admin. | Step 2 (uses is_org_admin) | Recreate the old is_org_member SELECT policy. | Medium — moderators lose audit visibility. Communicate to existing org members before deploy.
4 | App deploy | Ship /settings/members page (admin-gated). Wire to create_org_invite, revoke_org_invite, change_member_role, remove_org_member. | Steps 1-2 | Revert app deploy. | Low — page only visible to admins; existing members flow unaffected.
5 | Edge Function | Deploy 'send-invite' Edge Function. Try Supabase Auth admin.inviteUserByEmail(email, { redirectTo: app_url + '/invite/' + token }). If unavailable, fall back to Resend API call. Log delivery attempts. | Step 4 | Disable Edge Function. Admins can copy/paste invite link from UI as workaround. | Medium — depends on Lovable Cloud Edge Function support and SMTP availability.
6 | App deploy | Ship /invite/[token] page. Wire preview_invite + accept_org_invite. Add contextual signup path with emailRedirectTo back to the invite URL. | Steps 2, 5 | Revert app deploy. Existing accept_org_invite RPC still callable manually. | Medium — touches auth flow. Test acceptance with new-user and existing-user paths separately.
7 | App deploy | Ship /settings/audit page + diff modal + CSV export of filtered entries. | Step 3 | Revert app deploy. | Low — read-only viewer.
8 | Cleanup | Decide fate of private.promote_org_member: either deprecate (recommend) or keep as documented emergency backdoor for support engineers. | Step 4 in production for at least one week | n/a. | Low — cosmetic.

## Test Cases
# | Scenario | Steps | Expected | Notes
T1 | Invite happy path — new user | 1. Admin in org A creates invite for newuser@example.com with role=user. 2. App calls send-invite Edge Function -> email sent. 3. Newuser clicks link -> /invite/[token]. 4. Page shows 'Sign up as newuser@example.com'. 5. Newuser completes signup -> emailRedirectTo brings them back to /invite/[token] signed in. 6. Newuser clicks Accept. | org_members row inserted with (newuser_id, org_A, 'user'). Invite marked accepted_at. Redirect to /command. New audit row in member audit log (if Step 1.6 trigger added). | Re-test signup unblock surface: confirm /auth/v1/signup standalone still creates an unaffiliated user (Phase A property).
T2 | Invite happy path — existing user | 1. Admin invites existing-user@example.com. 2. Existing-user clicks link -> sees 'Sign in as existing-user@example.com'. 3. Signs in -> Accept button. 4. Accept. | org_members upsert: if user was already a member of org_A, role updates to invite.role; otherwise new row. | Verify ON CONFLICT (user_id, org_id) DO UPDATE SET role behavior is what's wanted (vs. error on duplicate).
T3 | Invite negative — expired | Admin creates invite. DB clock fast-forward (or alter expires_at to past). Invitee clicks link. | preview_invite returns status='expired'. Page shows expired message. accept_org_invite RPC also errors if called.
T4 | Invite negative — revoked | Admin creates then revokes invite. Invitee clicks link. | preview_invite returns status='revoked'. accept_org_invite errors.
T5 | Invite negative — wrong email | Admin invites a@example.com. User signs in as b@example.com and tries to accept. | accept_org_invite raises with 'invite email does not match auth email'. UI shows 'Please sign in as <email>'. | Case-insensitive comparison (lower()).
T6 | Invite negative — already accepted | Run T1 to completion. Invitee revisits link. | preview_invite returns status='accepted'. Page shows 'Already accepted, sign in to continue'.
T7 | Role change — self-demotion lockout guard | Admin tries to change own role from admin to moderator while being only admin. | change_member_role raises 'cannot demote last admin'.
T8 | Role change — self-demotion when other admin exists | Two admins exist. One self-demotes to moderator. | Succeeds. Org still has one admin.
T9 | Remove member — last admin guard | Org has one admin and one moderator. Admin tries to remove themselves (or be removed). | remove_org_member raises 'cannot remove self' and 'cannot remove last admin'.
T10 | Audit viewer — non-admin denied | Sign in as moderator. Direct-navigate to /settings/audit. Also call SELECT * FROM metric_audit_log via PostgREST. | Page redirects with 'no access'. PostgREST returns 0 rows (RLS denies). | Mirror of Phase A Test 2 methodology.
T11 | Audit viewer — admin can read own org | Sign in as admin. Visit /settings/audit. Apply date filter. | Rows returned for own org only. Diff modal renders. CSV export sanitizer applied. | Smoke-test export with a row whose notes='=1+1' to confirm escapeCsvCell still runs.
T12 | Audit viewer — admin cannot read other org | Admin of org A tries to read metric_audit_log rows belonging to org B (via filter param manipulation or direct PostgREST). | Zero rows returned. RLS denies cross-org reads.
T13 | Forge attempt regression | Re-run Phase A Test 2: authenticated non-admin POSTs to /rest/v1/metric_audit_log. | Still 401 code 42501 violates RLS. | Smoke test that Phase B migrations didn't loosen any policy by accident.
T14 | Signup unblock surface unchanged | From a clean browser, POST /auth/v1/signup directly with throwaway email. Sign in. Try to read health_metrics. | User created but no org_members row. health_metrics SELECT returns 0 rows. Phase A's accepted finding 1 mitigation still holds.
T15 | Email delivery — Supabase Auth path | Trigger create_org_invite -> send-invite Edge Function -> Supabase Auth admin.inviteUserByEmail. | Email arrives. Link contains the token. Clicking lands on /invite/[token]. | If Lovable Cloud blocks the admin API, this test fails and we trigger the Resend fallback.
T16 | Email delivery — Resend fallback | Configure Resend API key. Trigger create_org_invite. Verify Edge Function picks Resend path. | Email arrives via Resend. Same accept flow works. | Only run if T15 fails.